## Worksheet
Task | Start Date | End Date | Duration (Days) | Budget (USD) | Cost Progress (%) | Responsible Team
Market Research & Analysis | 2024-03-01 | 2024-03-15 | 15 | 15,000 | 85% | Marketing & Strategy Team
Product Feature Design (Phase 1) | 2024-03-16 | 2024-04-10 | 35 | 75,000 | 60% | Product Design & Engineering
Development & Coding (Beta) | 2024-04-11 | 2024-05-30 | 60 | 120,000 | 45% | Engineering & QA Team
User Testing & Feedback Loop | 2024-06-01 | 2024-06-30 | 30 | 35,000 | 95% | User Experience & Support
Final Product Launch Planning | 2024-07-01 | 2024-07-15 | 15 | 20,000 | 100% | Operations & Marketing