## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status
Project Kickoff Meeting | 2024-03-01 | 2024-03-01 | 1 | Sarah Johnson | Completed
Market Research Analysis | 2024-03-02 | 2024-03-15 | 14 | David Chen | In Progress
Product Requirements Finalization | 2024-03-16 | 2024-03-31 | 16 | Lisa Morgan | Planned
UI/UX Design Phase | 2024-04-01 | 2024-04-30 | 30 | Tom Williams | Scheduled
Development Sprint 1 | 2024-05-01 | 2024-05-15 | 15 | Team A (Engineering) | Not Started
Testing & Quality Assurance | 2024-05-16 | 2024-06-10 | 35 | Rachel Patel | Planned
Final Review & Deployment | 2024-06-11 | 2024-06-15 | 5 | Executive Team | Scheduled