## Worksheet
Task | Start Date | End Date | Duration | Responsible | Progress (%)
Project Kickoff & Planning | 2024-03-01 | 2024-03-15 | 15 days | Manager A | 100%
Market Research & Analysis | 2024-03-16 | 2024-04-10 | 35 days | Team B | 75%
Product Design & Prototyping | 2024-04-11 | 2024-05-30 | 60 days | Designer C | 50%
Development Phase (Phase 1) | 2024-06-01 | 2024-07-15 | 65 days | Dev Team D | 30%
Testing & Quality Assurance | 2024-07-16 | 2024-08-31 | 56 days | QA Team E | 20%
Launch Preparation & Training | 2024-09-01 | 2024-09-30 | 30 days | Manager A & Team F | 10%
Official Product Launch | 2024-10-01 | 2024-10-03 | 3 days | All Teams | 100%