## Worksheet
Task | Start Date | End Date | Duration (Days) | Status
Project Kickoff Meeting | 2023-10-01 | 2023-10-01 | 1 | Completed
Define Productivity Goals | 2023-10-02 | 2023-10-05 | 4 | In Progress
Team Training on Tools | 2023-10-06 | 2023-10-10 | 5 | Planned
Optimize Workflow Processes | 2023-10-11 | 2023-10-25 | 15 | Scheduled
Performance Review & Adjustment | 2023-10-26 | 2023-10-30 | 5 | Planned
Monthly Progress Report & Feedback | 2023-11-01 | 2023-11-01 | 1 | Scheduled
Team Retrospective & Planning | 2023-11-02 | 2023-11-06 | 5 | Scheduled