## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Party | Progress (%)
Project Planning & Scope Definition | 2024-03-01 | 2024-03-15 | 15 | Project Manager | 100
Team Training & Onboarding | 2024-03-16 | 2024-03-31 | 16 | HR & Operations Lead | 95
Process Workflow Design | 2024-04-01 | 2024-04-15 | 15 | Process Analyst | 80
Technology Stack Selection & Setup | 2024-04-16 | 2024-05-10 | 35 | IT Infrastructure Team | 70
Pilot Implementation (Phase 1) | 2024-05-11 | 2024-06-05 | 35 | Operations Team | 40
Performance Monitoring & Feedback Loop | 2024-06-06 | 2024-07-15 | 30 | Productivity Analysts | 65
Full-Scale Rollout & Optimization | 2024-07-16 | 2024-09-30 | 75 | All Departments | 0
Total Duration |  |  | 295 days | Overall Progress: 68%