## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Project Planning & Initiation | 2024-01-01 | 2024-01-15 | 15 | Project Manager | Completed
Team Training & Onboarding | 2024-01-16 | 2024-01-31 | 16 | HR Department | In Progress
Process Workflow Optimization | 2024-02-01 | 2024-03-15 | 65 | Operations Team | Not Started
Tool Implementation & Integration | 2024-03-16 | 2024-04-30 | 55 | IT Department | Scheduled
Performance Review & Reporting Setup | 2024-05-01 | 2024-05-31 | 31 | Analytics Team | Not Started
Final Review & Rollout | 2024-06-01 | 2024-06-30 | 30 | Project Manager | Planned