## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Progress (%)
Productivity Assessment & Baseline Analysis | 2024-03-01 | 2024-03-15 | 15 | John Doe | 100%
Process Mapping & Workflow Review | 2024-03-16 | 2024-04-05 | 21 | Jane Smith | 85%
Implement Time Management Tools | 2024-04-06 | 2024-05-10 | 35 | Mike Johnson | 60%
Employee Training on Productivity Techniques | 2024-05-11 | 2024-06-15 | 45 | Sarah Lee | 30%
Performance Review & Optimization Cycle | 2024-06-16 | 2024-07-31 | 46 | Team Lead | 0%