## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Project Kickoff & Planning | 2024-03-01 | 2024-03-05 | 5 | Project Manager | Completed
Market Research & Analysis | 2024-03-06 | 2024-03-15 | 10 | Marketing Team | In Progress
Product Design & Prototyping | 2024-03-16 | 2024-04-10 | 25 | Design Team | Not Started
Development & Coding Phase | 2024-04-11 | 2024-05-30 | 50 | Engineering Team | Not Started
QA Testing & Bug Fixes | 2024-06-01 | 2024-06-15 | 15 | QA Team | Not Started
User Training & Onboarding | 2024-06-16 | 2024-06-30 | 15 | Training Officer | Not Started
Project Review & Final Delivery | 2024-07-01 | 2024-07-10 | 10 | Project Manager | Not Started