## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status
Project Planning & Scope Definition | 2024-03-01 | 2024-03-15 | 15 | John Smith | Completed
Market Research & Analysis | 2024-03-16 | 2024-04-05 | 21 | Sarah Lee | In Progress
Product Design & Prototyping | 2024-04-06 | 2024-05-10 | 35 | Mike Chen | Not Started
Development & Testing Phase | 2024-05-11 | 2024-07-15 | 66 | Team A (Dev) | Not Started
User Training & Documentation | 2024-07-16 | 2024-08-05 | 21 | Linda Park | Not Started
Final Review & Go-Live | 2024-08-06 | 2024-08-31 | 26 | Project Manager | Not Started