## Worksheet
Task | Start Date | End Date
Productivity Improvement Initiative | Q1 2024 – Q3 2024
Define Productivity Goals & KPIs | Mar 1, 2024 | Mar 15, 2024
Employee Feedback Survey (Team A) | Apr 5, 2024 | Apr 18, 2024
Analyze Current Workflows | May 1, 2024 | May 30, 2024
Implement Time Management Tools (e.g., Trello) | Jun 1, 2024 | Jul 15, 2024
Pilot Task Automation for Reporting | Aug 1, 2024 | Aug 30, 2024
Training Sessions on Productivity Techniques | Sep 5, 2024 | Sep 30, 2024
Measure Progress & Adjust Strategies | Oct 1, 2024 | Nov 15, 2024
Final Review & Sustainable Practices Rollout | Dec 1, 2024 | Dec 31, 2024
Total Duration: 10 Months