## Worksheet
Task | Start Date | End Date | Status | Progress (%)
Project Planning Phase | 2024-03-01 | 2024-03-15 | In Progress | 65%
Process Mapping & Analysis | 2024-03-16 | 2024-04-05 | Pending Start | -
Tool Selection & Evaluation | 2024-04-06 | 2024-04-25 | Not Started | -
Pilot Implementation (Team A) | 2024-05-01 | 2024-05-31 | Planned | -
Performance Metrics Setup | 2024-06-01 | 2024-06-30 | In Progress | 45%
Full-Scale Rollout | 2024-07-01 | 2024-08-31 | Not Started | -
Review & Optimization Phase | 2024-09-01 | 2024-10-31 | Pending Start | -
Gantt Chart – Productivity Improvement ¦ Report Version
Generated for internal use. Data updated as of May 2024.