## Worksheet
Task | Start Date | End Date | Duration (Days) | Status
Define Productivity Goals | 2024-03-01 | 2024-03-05 | 5 | Completed
Conduct Employee Productivity Audit | 2024-03-06 | 2024-03-15 | 10 | In Progress
Implement Time Tracking System | 2024-03-16 | 2024-04-10 | 35 | Not Started
Train Employees on New Tools | 2024-04-11 | 2024-04-25 | 15 | Planned
Review and Optimize Workflows | 2024-04-26 | 2024-05-10 | 15 | Not Started
Measure Impact and Adjust Strategy | 2024-05-11 | 2024-05-31 | 30 | Planned