## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible | Status
Market Research & Analysis | 2024-03-15 | 2024-03-25 | 10 | Marketing Team | In Progress
Product Feature Definition | 2024-03-26 | 2024-04-10 | 15 | Product Manager | Not Started
UI/UX Design Phase | 2024-04-11 | 2024-04-30 | 30 | Design Team | Planned
Development & Coding | 2024-05-01 | 2024-06-15 | 60 | Engineering Team | Not Started
Testing & Quality Assurance | 2024-06-16 | 2024-07-10 | 35 | QA Team | Not Started
Launch Preparation & Training | 2024-07-11 | 2024-07-31 | 30 | Operations Team | Not Started
Post-Launch Review & Optimization | 2024-08-01 | 2024-08-15 | 15 | Project Manager | Not Started