## Worksheet
Task | Start Date | End Date | Duration | Progress (%) | Owner
Project Kickoff & Planning | 2024-03-01 | 2024-03-15 | 15 days | 85% | Alex Morgan
Market Research & Analysis | 2024-03-16 | 2024-04-10 | 35 days | 60% | Samira Chen
Product Design & Wireframing | 2024-04-11 | 2024-05-15 | 45 days | 30% | Jordan Lee
Development Phase (MVP) | 2024-05-16 | 2024-07-31 | 97 days | 15% | Team Lead Ravi Patel
User Testing & Feedback Loop | 2024-08-01 | 2024-08-31 | 31 days | 5% | Lena Torres
Launch & Post-Launch Review | 2024-09-01 | 2024-09-30 | 30 days | 0% | All Team