## Worksheet
Task | Start Date | End Date | Duration | Responsible | Status
Project Planning & Kickoff | 2024-03-01 | 2024-03-15 | 15 days | Project Manager | Completed
Market Research & Analysis | 2024-03-16 | 2024-04-10 | 35 days | Research Lead | In Progress
Product Design & Prototyping | 2024-04-11 | 2024-05-30 | 60 days | Design Team | Not Started
Development & Coding Phase | 2024-06-01 | 2024-08-15 | 95 days | Engineering Team | Not Started
Quality Assurance & Testing | 2024-08-16 | 2024-09-30 | 45 days | QA Manager | Not Started
User Training & Rollout | 2024-10-01 | 2024-10-31 | 31 days | Training Coordinator | Not Started
Post-Launch Review & Optimization | 2024-11-01 | 2024-11-30 | 30 days | Operations Lead | Not Started