## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Team Member | Status
Project Kickoff Meeting | 2024-04-01 | 2024-04-01 | 1 | Project Management Team | Completed
Requirement Gathering Workshop | 2024-04-02 | 2024-04-05 | 4 | Product & UX Team | In Progress
Product Design Phase | 2024-04-06 | 2024-04-15 | 10 | Design Team | Planned
Development Sprint 1 | 2024-04-16 | 2024-04-25 | 10 | Engineering Team | Not Started
Testing & Quality Assurance | 2024-04-26 | 2024-05-05 | 10 | QA Team | Planned
User Training & Onboarding | 2024-05-06 | 2024-05-10 | 5 | Support & Training Team | Not Started
Project Review & Closure | 2024-05-11 | 2024-05-11 | 1 | Project Management Team | Planned