## Worksheet
Task | Start Date | End Date | Duration (Days) | Responsible Person | Status
Market Research | 2024-04-01 | 2024-04-15 | 15 | Jane Smith | In Progress
Product Design Finalization | 2024-04-16 | 2024-05-10 | 35 | Mark Johnson | Pending Start
Development Phase (Alpha) | 2024-05-11 | 2024-06-15 | 45 | Lisa Chen | Not Started
User Testing & Feedback Collection | 2024-06-16 | 2024-07-10 | 35 | Sam Wilson | Scheduled
Final Review & Launch Preparation | 2024-07-11 | 2024-07-31 | 31 | Natalie Brown | Planned
Productivity Improvement – Gantt Chart Template Version