## Worksheet
Task | Start Date | End Date | Status | Progress (%) | Responsible Person
Project Planning & Scope Definition | 2024-03-01 | 2024-03-15 | Completed | 100% | Jane Smith
Market Research & Analysis | 2024-03-16 | 2024-04-10 | In Progress | 75% | Alex Johnson
Product Design & Prototyping | 2024-04-11 | 2024-05-30 | Not Started | 0% | Sarah Lee
Development & Testing Phase | 2024-06-01 | 2024-07-31 | Not Started | 0% | Mike Taylor
User Training & Onboarding | 2024-08-01 | 2024-08-15 | Not Started | 0% | Lisa Wong
Performance Review & Optimization | 2024-08-16 | 2024-09-30 | Not Started | 0% | David Brown