## Worksheet
Date | Task | Assigned To | Priority | Status | Estimated Time (hrs) | Actual Time (hrs) | Progress (%)
2024-04-01 | Project Planning Meeting | Alex Morgan | High | Completed | 2 | 2 | 100%
2024-04-03 | Design Wireframes | Samira Patel | High | In Progress | 4.5 | 3 | 67%
2024-04-05 | Develop Backend API | James Reed | Critical | Not Started | 8 | 0 | 0%
2024-04-07 | User Testing Session | Taylor Kim | Medium | Scheduled | 3 | 0 | 0%
2024-04-10 | Performance Optimization | Mia Chen | High | Not Started | 5 | 0 | 0%