## Maintenance Log - Manager View
Productivity Improvement - Maintenance Log (Manager View)
Date | Task Name | Description | Assigned To | Status | Priority Level | Estimated Time (hrs) th> | Actual Time (hrs) th> | Last Updated
2024-04-01 | Optimize Workflow Process | Review current workflow and identify bottlenecks to reduce cycle time by 15%. | Jane Smith | In Progress | High | 8 | 6.5 | 2024-04-03
2024-04-05 | Cleanup Old Project Files | Migrate and archive outdated project documents to cloud storage. | Michael Lee | Completed | Moderate | 3 | 3 | 2024-04-05
2024-04-10 | Team Training Session on Tools | Scheduled session to train team on new productivity software. | Sarah Chen | Pending | High | 5 | 0 | 2024-04-10
2024-04-15 | Evaluate Time Tracking System | Analyze current time tracking tools and recommend improvements. | David Kim | In Review | Medium | 6 | 0 | 2024-04-15