## Worksheet
Date | Task Description | Assigned To | Status | Priority | Estimated Time (hrs) | Actual Time (hrs) | Completion Notes
01/04/2024 | Optimize daily workflow using time-tracking tools | John Smith | Completed | High | 2.5 | 2 | Workflow improved by 15%; saved 40 minutes daily.
01/10/2024 | Set up automated report generation | Sarah Lee | In Progress | High | 4 | - | Integration with Excel and email is underway.
01/15/2024 | Conduct team productivity audit | Mike Chen | Completed | Medium | 5 | 4.8 | Identified bottlenecks in email handling and meetings.
01/20/2024 | Implement focus time blocks for team meetings | Anna Rodriguez | Planned | High | 6 | - | Scheduled for next sprint planning session.