## Worksheet
Order ID | Client Name | Project Title | Due Date | Priority Level | Status | Estimated Hours | Actual Hours | Progress (%) | Next Action
ORD-2024-001 | Sarah Thompson | Website Redesign for EcoStore | 2024-05-30 | High | In Progress | 80 | 65 | 81% | Finalize UI mockups by May 25
ORD-2024-002 | David Kim | Content Strategy for TechBlog | 2024-06-15 | Medium | Pending | 40 | 0 | 0% | Schedule kickoff meeting
ORD-2024-003 | Lisa Chen | Social Media Campaign – Q2 | 2024-07-10 | High | Completed | 50 | 50 | 100% | Submit analytics report
ORD-2024-004 | James Wilson | Email Automation Setup | 2024-06-28 | Medium | On Hold | 30 | 10 | 33% | Review requirements with client