## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Resources Required | Dependencies | Milestones | Notes
Define Productivity Goals | Jane Doe | 2024-03-01 | 2024-03-15 | In Progress | High | Project Manager, HR Team |  |  | Align with organizational objectives and employee feedback.
Conduct Employee Productivity Audit | John Smith | <2024-03-16 | 2024-04-05 | Not Started | High | Data Analyst, IT Support | Goal Definition Complete | Audit Completion Milestone | Review current workflows and usage patterns.
Develop Productivity Tools & Workflow Templates | Lisa Chen | 2024-04-06 | 2024-05-31 | Not Started | Medium | Design Team, Operations Staff | Audit Results Available |  | Create standardized templates for daily tasks.
Train Employees on New Tools | Mike Johnson | 2024-06-01 | 2024-06-30 | Not Started | Medium | Training Coordinator, Department Heads | Tools Developed & Tested | Training Completion Milestone | Offer hands-on workshops and documentation.
Measure Impact & Adjust Strategy | Jane Doe | 2024-07-01 | 2024-08-31 | Not Started | High | Analytics Team, Leadership Committee | <Training Completed & Feedback Collected | Final Impact Review Milestone | Evaluate KPIs and refine processes based on results.