## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Resources Required | Milestones
Conduct Productivity Audit | Jane Smith | 2024-01-15 | 2024-01-31 | In Progress | High | Analytics Team, HR | Audit Complete
Implement Task Management System | Mike Johnson | 2024-02-01 | 2024-03-15 | Planned | High | IT, Project Management Office | System Deployment Finalized
Train Employees on New Tools | Sarah Lee | 2024-03-20 | 2024-04-10 | Scheduled | Medium | L&D Department, All Teams | Training Completion
Optimize Workflow Processes | David Chen | 2024-04-15 | 2024-06-30 | In Progress | High | Operations, Process Engineers | Process Redesign Approved
Monitor and Review Performance Metrics | Lisa Wong | 2024-07-01 | 2024-12-31 | Planned | Medium | Data Analytics, Management Team | Quarterly Review Meetings
Total Tasks: |  |  |  | 5