## Worksheet
Task | Owner | Start Date | End Date | Status | Priority
Define Productivity Goals | John Doe | 2024-04-01 | 2024-04-10 | In Progress | High
Conduct Employee Productivity Survey | Jane Smith | 2024-04-11 | 2024-04-18 | Pending | Medium
Analyze Current Workflow Processes | Michael Brown | 2024-04-19 | 2024-05-03 | Not Started | High
Develop Process Optimization Plan | Lisa Chen | 2024-05-04 | 2024-05-17 | Pending | High
Implement New Tools and Software | Robert Kim | 2024-05-18 | 2024-06-15 | Not Started | High
Evaluate and Measure Impact | All Team Members | 2024-06-16 | 2024-07-10 | Not Started | Medium