## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Dependencies | Progress (%)
Define Productivity Goals | Jane Doe | 2024-04-01 | 2024-04-15 | Completed | High | None | 100%
Conduct Employee Needs Assessment | John Smith | 2024-04-16 | 2024-05-03 | In Progress | High | Goal Definition | 65%
Identify Productivity Tools | Lisa Chen | 2024-05-04 | 2024-05-18 | Not Started | Medium | Needs Assessment | 0%
Develop Training Program | Mark Lee | 2024-05-19 | 2024-06-30 | Planned | High | Tool Selection | 0%
Implement New Work Processes | Sarah Kim | 2024-07-01 | 2024-08-31 | Not Started | Critical | Training Completion | 0%