## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Dependencies
Define Productivity Goals | Sarah Johnson | 2024-03-01 | 2024-03-15 | Completed | 100% | None
Conduct Stakeholder Interviews | Michael Chen | 2024-03-16 | 2024-03-31 | In Progress | 65% | Goal Definition
Develop Productivity Workflow Framework | Lisa Park | 2024-04-01 | 2024-04-15 | Not Started | 0% | Stakeholder Interviews
Implement Tools & Automation | David Miller | 2024-04-16 | 2024-05-31 | Planned | 0% | Workflow Framework
Evaluate Performance & Adjust | Team Lead | 2024-06-01 | 2024-06-30 | Not Started | 0% | Tool Implementation