## Worksheet
Task | Owner | Start Date | End Date | Status | Priority
Define Productivity Goals | Jane Smith | 2024-04-01 | 2024-04-05 | Completed | High
Analyze Current Workflows | John Doe | 2024-04-06 | 2024-04-15 | In Progress | Middle
Identify Time-Wasting Activities | Lisa Chen | 2024-04-16 | 2024-04-25 | Pending | High
Implement Tools & Software | Mark Wilson | 2024-05-01 | 2024-05-31 | Pending | High
Train Team on New Processes | Sarah Lee | 2024-06-01 | 2024-06-15 | Pending | Middle
Evaluate Results & Adjust Plan | Team Lead | 2024-07-01 | 2024-07-31 | Pending | High