## Worksheet
Project Phase | Objective | Key Activities | Responsible Team | Start Date | End Date | Status | Progress (%)
Initiation | Define project scope, goals, and success metrics. | Stakeholder interviews, SWOT analysis, requirement gathering. | Project Office | 01/15/2024 | 02/15/2024 | Completed | 100%
Planning | Develop detailed work breakdown, timelines, and resources. | Task decomposition, resource allocation, risk assessment. | Operations & Strategy | 02/16/2024 | 03/31/2024 | In Progress | 65%
Execution | Implement productivity tools and workflows. | Tool onboarding, workflow training, pilot launch. | IT & Productivity Team | 04/01/2024 | 06/30/2024 | Not Started | 0%
Monitoring & Review | Track KPIs and adjust strategies based on performance. | Weekly reviews, dashboard updates, performance reports. | Analytics & Leadership | 07/01/2024 | 12/31/2024 | Not Started | 0%
Closure | Formalize outcomes, document lessons learned. | Final review, stakeholder sign-off, knowledge transfer. | Project Office | 01/01/2025 | 01/31/2025 | Not Started | 0%