## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Dependencies | Notes
Define Productivity Goals | Jane Smith | 2024-03-01 | 2024-03-15 | Completed | 100% | - | Aligned with organizational objectives.
Conduct Stakeholder Analysis | John Doe | 2024-03-16 | 2024-03-31 | In Progress | 75% | Goal Definition | Meeting with department leads scheduled for 03-25.
Select Productivity Tools | Alex Chen | 2024-04-01 | 2024-04-15 | Not Started | 0% | Stakeholder Analysis Complete | Evaluate options including Trello, Asana, and ClickUp.
Train Employees on New Tools | Sarah Lee | 2024-05-01 | 2024-05-31 | Planned | 0% | Tool Selection Complete | Schedule workshops and documentation.
Monitor & Evaluate Performance | Mike Brown | 2024-06-01 | 2024-07-31 | Not Started | 0% | Tool Implementation Complete | Weekly reports will be collected and analyzed.