## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Progress (%) | Notes
Define Productivity Goals | Jane Doe | 2024-04-01 | 2024-04-15 | In Progress | High | 60% | Align with company strategy and KPIs
Conduct Employee Survey | John Smith | 2024-04-10 | 2024-04-25 | Not Started | Medium | 0% | Distribute via email and in-person forms
Analyze Current Workflows | Lisa Chen | 2024-05-01 | 2024-05-15 | Not Started | High | 0% | Review process maps and time logs
Implement Automation Tools | Mark Johnson | 2024-06-01 | 2024-07-31 | Not Started | High | 0% | Select and deploy tools like Zapier or Power Automate
Train Employees on New Tools | Sarah Lee | 2024-07-15 | 2024-08-15 | Not Started | Medium | 0% | Schedule sessions and create guides
Monitor & Review Productivity Metrics | Jane Doe | 2024-08-01 | 2024-10-31 | Not Started | High | 0% | Monthly reports and adjustments based on results