## Worksheet
Task ID | Task Name | Owner | Start Date | End Date | Duration (days) | Priority | Status | Dependencies | Resources Required | Milestones | Risk Assessment
P00115HighIn ProgressNoneKickoff Meeting (Day 1)Low - Risk of scope creep
P00225MediumPlannedP001Final Report Due (Day 25)Medium - Data access delays possible
P00351HighNot StartedP002Prototype Review (Day 30)High - Design validation challenges
P00460HighPlannedP003, P005Alpha Release (Day 45)Medium - Integration bugs possible
P00515HighScheduledP004Final Test Report (Day 15)High - Critical bug discovery risk
P00616CriticalNot StartedP005Live Launch (Day 16)Critical - Downtime risk