## Worksheet
Task | Owner | Start Date | End Date | Duration (Days) | Budget (USD) | Status | Progress (%)
Market Research & Analysis | Sarah Chen | 2024-03-15 | 2024-03-30 | 15 | 15,000 | On Track | 85%
Product Feature Development | David Kim | 2024-04-01 | 2024-05-15 | 56 | 75,000 | In Progress | 60%
User Testing & Feedback Loop | Lisa Wong | 2024-05-16 | 2024-06-10 | 35 | 30,000 | Not Started | 0%
Performance Optimization | James Patel | 2024-06-11 | 2024-07-30 | 60 | 45,000 | Not Started | 0%
Final Review & Launch Preparation | Team Lead | 2024-08-01 | 2024-08-15 | 15 | 10,000 | Not Started | 0%
Total Budget: |  |  |  | $175,000