## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Notes
Define Productivity Goals | Jane Doe | 2024-04-01 | 2024-04-05 | Completed | 100% | Set SMART goals for team efficiency.
Conduct Time Audit | John Smith | 2024-04-062024-04-10 | In Progress | 65% | Analyzing daily work logs and idle time.
Implement Task Automation Tools | Sarah Lee | 2024-04-11 | 2024-04-25 | Pending | 0% | Identify and deploy automation scripts for repetitive tasks.
Conduct Team Training Workshops | Mike Chen | 2024-04-26 | 2024-05-03 | Not Started | 0% | Focus on time management and priority setting.
Evaluate Weekly Productivity Metrics | All Team Members | 2024-05-04 | 2024-05-17 | Not Started | 0% | Review KPIs and adjust strategies accordingly.