## Worksheet
Task | Responsible Person | Start Date | End Date | Status | Priority | Progress (%) | Dependencies
Market Research & Analysis | Jane Doe | 2024-03-01 | 2024-03-15 | In Progress | High | 60% | None
Product Design & Prototyping | Mark Smith | 2024-03-16 | 2024-04-10 | Planned | High | 0% | Market Research
Development & Testing | Alex Chen | 2024-04-11 | 2024-05-30 | Not Started | Critical | 0% | Product Design
Training & Onboarding | Sarah Lee | 2024-06-01 | 2024-06-15 | Planned | Medium | 0% | Development & Testing
Launch & Post-Launch Review | Team Leadership | 2024-07-01 | 2024-07-31 | Not Started | High | 0% | Training & Onboarding