## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Dependencies | Notes
Define Productivity Goals | Jane Smith | 2024-03-01 | 2024-03-15 | Completed | 100% | - | Established key performance indicators and team objectives.
Conduct Employee Productivity Audit | Mike Johnson | 2024-03-16 | 2024-04-05 | In Progress | 65% | Goal Definition | Gathering data from time logs and performance reviews.
Implement Workflow Automation Tools | Sarah Lee | 2024-04-06 | 2024-05-31 | Not Started | 0% | Audit Results | Evaluate tools and select top 3 for rollout.
Train Teams on New Tools | David Kim | 2024-06-01 | 2024-06-30 | Not Started | 0% | Tool Implementation | Schedule sessions for all departments.
Monitor and Evaluate Impact | Jane Smith | 2024-07-01 | 2024-08-31 | Not Started | 0% | Training Completion | Monthly review of KPIs and user feedback.