## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Dependencies | Notes
Define Productivity Goals for the Month | Jane Smith | 2023-10-01 | 2023-10-05 | Completed | 100% | - | Aligned with departmental objectives.
Conduct Team Productivity Audit | Mark Johnson | 2023-10-06 | 2023-10-12 | In Progress | 75% | Goal Definition | Reviewing workflow patterns and tool usage.
Implement Time-Tracking System | Lisa Chen | 2023-10-13 | 2023-10-25 | Not Started | 0% | Audit Results | Pilot with 3 teams before full rollout.
Train Team on New Productivity Tools | David Park | 2023-10-26 | 2023-11-03 | Scheduled | 0% | Tool Implementation | Sessions scheduled for Monday and Friday.
Evaluate Monthly Productivity Metrics | Jane Smith | 2023-11-04 | 2023-11-10 | Not Started | 0% | Tool Implementation & Training | Generate performance reports and feedback.