## Worksheet
Project Phase | Objective | Key Activities | Responsible Party | Start Date | End Date | Status | Notes/Comments
Phase 1: Needs Assessment | Identify current productivity bottlenecks and employee workflows. | Interview staff, analyze workflow maps, collect performance data. | Project Manager & HR Team | 2024-03-01 | 2024-03-15 | Completed | No major issues identified; data collection was successful.
Phase 2: Solution Design | Develop tailored productivity tools and procedures based on findings. | Workshops, prototype development, tool selection criteria. | Productivity Analyst & Engineering Team | <2024-03-16 | 2024-04-10 | In Progress | Two tool prototypes under review.
Phase 3: Pilot Implementation | Test the solution in a controlled environment with select teams.Pilot deployment, user feedback collection, monitoring KPIs. | Operations Lead & IT Department | 2024-04-11 | 2024-05-05 | Pending Approval | Pilot group of 15 employees; feedback to be gathered.
Phase 4: Full Rollout | Deploy productivity tools across all departments. | Training sessions, system integration, change management. | Project Manager & Department Heads | 2024-05-06 | 2024-06-30 | Not Started | All training materials ready; rollout schedule pending budget sign-off.
Phase 5: Evaluation & Optimization | Measure impact, gather long-term feedback, refine processes. | Performance reviews, analytics reporting, continuous improvement plan. | Quality Assurance Team & Analytics Unit | 2024-07-01 | 2024-08-31 | Not Started | A quarterly review framework will be established.