## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Dependencies | Notes
Define Productivity Goals | John Smith | 2024-03-01 | 2024-03-15 | Completed | 100% | - | Set measurable KPIs for team output.
Conduct Employee Productivity Audit | Lisa Chen | 2024-03-16 | 2024-04-05 | In Progress | 65% | Goal Definition | Survey and analyze current workflow patterns.
Identify Tools & Technologies | Mark Taylor | 2024-04-06 | 2024-04-18 | Not Started | 0% | - | Evaluate software solutions for workflow optimization.
Train Team on New Tools | Sarah Kim | 2024-04-20 | 2024-05-10 | Planned | 0% | Tool Selection | Schedule workshops and sessions.
Measure Impact & Adjust Strategy | John Smith | 2024-05-11 | 2024-06-30 | Not Started | 0% | Tool Training, Audit Results | Review KPIs and refine approach based on data.