## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Progress (%)
Define Productivity Goals | Alex Morgan | 2024-03-01 | 2024-03-07 | Completed | High | 100%
Conduct Workflow Analysis | Jordan Lee | 2024-03-08 | 2024-03-15 | In Progress | High | 65%
Implement Time-Tracking Tools | Samira Patel | 2024-03-16 | 2024-03-30 | Not Started | High | 0%
Train Team on New Tools | Marcus Chen | 2024-04-01 | 2024-04-10 | Planned | Medium | 0%
Review Productivity Metrics | Rita Singh | 2024-04-15 | 2024-04-30 | Not Started | Medium | 0%
Optimize Daily Routines | Taylor Kim | 2024-05-01 | 2024-05-31 | Planned | High | 0%