## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Dependencies | Priority
Define Productivity Goals | Jane Doe | 2024-03-15 | 2024-03-18 | Completed | 100% |  | High
Conduct Stakeholder Interviews | John Smith | 2024-03-19 | 2024-03-25 | In Progress | 75% | Define Goals | Medium
Analyze Current Workflows | Lisa Chen | 2024-03-26 | 2024-04-01 | Not Started | 0% |  | High
Develop Productivity Tools | Mike Brown | 2024-04-02 | 2024-05-15 | Not Started | 0% | Workflow Analysis | Critical
Train Users on New Tools | Sarah Lee | 2024-05-16 | 2024-05-31 | Not Started | 0% | Tools Development | Medium
Measure & Review Productivity Impact | Team Lead | 2024-06-01 | 2024-06-30 | Not Started | 0% |  | High