## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Resources Required
Define Productivity Goals | Jane Smith | 2024-03-01 | 2024-03-15 | In Progress | High | Project Manager, HR Team
Conduct Employee Productivity Survey | John Doe | <2024-03-16 | 2024-03-31 | Not Started | High | Survey Tools, IT Support
Implement Time Tracking Software | Lisa Chen | 2024-04-01 | 2024-05-30 | Not Started | Critical | IT Team, Finance Department
Train Employees on New Tools | Michael Brown | 2024-06-01 | 2024-06-30 | Not Started | Medium | Training Coordinator, HR Team
Review and Adjust Workflows | Sarah Lee | 2024-07-01 | 2024-08-31 | Not Started | High | Operations Team, Process Analysts