## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Dependencies | Priority
Define Productivity Goals | Jane Doe | 2024-03-01 | 2024-03-15 | Completed | 100% | None | High
Conduct Team Productivity Assessment | John Smith | 2024-03-16 | 2024-03-30 | In Progress | 65% | Define Goals | High
Implement Time Management Tools | Alex Rivera | 2024-04-01 | 2024-04-30 | Planned | 0% | Team Assessment Complete | Medium
Train Team on New Productivity Methods | Sarah Kim | 2024-05-01 | 2024-05-31 | Not Started | 0% | Tools Implemented | High
Monitor and Evaluate Productivity Metrics | Mike Johnson | 2024-06-01 | 2024-06-30 | Planned | 0% | Training Complete | Medium