## Worksheet
Project Phase | Quarter | Objective | Key Activities | Responsible Team | Milestones | Timeline (DD/MM/YYYY) | Success Metrics
Q1 - Strategy & Planning | Q1 | Define productivity goals and align with business objectives. | - Conduct stakeholder interviews - Analyze current workflows - Identify inefficiencies | Productivity Task Force | Finalize productivity roadmap | 01/04/2024 – 30/06/2024 | 85% workflow clarity improvement
Q2 - Process Optimization | Q2 | Streamline core operational processes using data-driven insights. | - Implement automation tools - Redesign task workflows - Conduct pilot testing | Operations & Engineering | Complete 3 process pilots | 01/07/2024 – 31/09/2024 | 25% reduction in average task time
Q3 - Tool Integration & Training | Q3 | Integrate productivity tools and train teams on best practices. | - Deploy new software suite - Conduct training sessions - Collect user feedback | HR & IT Support | All team members trained and certified | 01/10/2024 – 30/12/2024 | 95% employee adoption rate
Q4 - Review & Sustainability | Q4 | Evaluate outcomes and establish long-term productivity protocols. | - Performance review meeting - Publish improvement report - Recommend future initiatives | Executive Steering Committee | Final report approved and shared | 01/01/2025 – 31/03/2025 | Sustained productivity growth of 15% YoY