## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Dependencies | Milestones
Define Productivity Goals | Jane Doe | 2024-03-01 | 2024-03-15 | Completed | 100% | - | Goal Set
Conduct Stakeholder Interviews | John Smith | 2024-03-16 | 2024-03-31 | In Progress | 60% | Goal Definition | -
Design Productivity Workflow | Lisa Chen | 2024-04-01 | 2024-04-15 | Not Started | 0% | Stakeholder Interviews | Workflow Draft Ready
Develop Tools & Templates | Mark Taylor | 2024-04-16 | 2024-05-10 | Not Started | 0% | Workflow Design | -
Train Team on New Tools | Sarah Lee | 2024-05-11 | 2024-05-25 | Not Started | 0% | Tools Developed | Training Complete
Measure & Review Productivity Impact | Alex Brown | 2024-05-26 | 2024-06-15 | Not Started | 0% | Training Complete | Final Review