## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%)
Define Productivity Goals | John Smith | 2024-03-01 | 2024-03-15 | Completed | 100%
Conduct Team Productivity Audit | Sarah Lee | 2024-03-16 | 2024-03-31 | In Progress | 65%
Implement Time Management Tools | Mike Johnson | 2024-04-01 | 2024-04-30 | Not Started | 0%
Train Team on New Tools | Lisa Wong | 2024-05-01 | 2024-05-15 | Not Started | 0%
Measure and Review Productivity Metrics | Admin Team | 2024-06-01 | 2024-06-30 | Not Started | 0%