## Small Business Project Plan
Productivity Improvement Project Plan
Task | Description | Responsible Person | Start Date | End Date th> | Status
Conduct Workflow Audit | Analyze current processes to identify inefficiencies. | Jane Smith | 2024-04-01 | 2024-04-15 | In Progress
Implement Time Management Tools | Introduce task tracking software for team use. | Mark Johnson | 2024-04-16 | 2024-05-10 | Pending
Train Team on New Tools | Organize workshops for staff to learn productivity tools. | Lisa Chen | 2024-05-11 | 2024-05-25 | Not Started
Evaluate Productivity Metrics | Measure output, time saved, and team feedback. | Mark Johnson | 2024-06-01 | 2024-06-30 | Pending
Adjust Processes Based on Data | Refine workflows using collected performance data. | Jane Smith | 2024-07-01 | 2024-07-31 | Not Started