## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Progress (%) | Dependencies
Define Productivity Goals | Sarah Lee | 2024-03-15 | 2024-03-20 | In Progress | High | 65% | None
Conduct Team Productivity Audit | James Wong | <2024-03-21 | 2024-03-28 | Planned | Medium | 0% | Goal Definition Complete
Implement Time Tracking Tools | Maria Garcia | 2024-04-01 | 2024-04-15 | Not Started | High | 0% | Audit Results Available
Develop Daily Stand-up Guidelines | David Chen | 2024-04-16 | 2024-04-30 | Planned | Medium | 0% | Tools Implemented
Review and Adjust Workflow Processes | Team Leadership Group | 2024-05-01 | 2024-05-15 | Not Started | High | 0% | Daily Stand-ups Live