## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Dependencies | Priority
Define Productivity Goals | Jane Smith | 2024-03-01 | 2024-03-15 | In Progress | 65% | - | High
Conduct Employee Surveys | John Doe | <2024-03-16 | 2024-03-31 | Not Started | 0% | Define Goals | Medium
Implement Time Tracking Tool | Lisa Chen | 2024-04-01 | 2024-04-30 | Planned | 0% | Survey Results | High
Train Team on New Tools | Mike Wilson | 2024-05-01 | 2024-05-15 | Not Started | 0% | Tool Implementation | Medium
Review Monthly Productivity Reports | Sarah Lee | 2024-06-01 | 2024-06-30 | Planned | 0% | Tool Training Complete | Low