## Worksheet
Week | Project Phase | Key Objective | Assigned Team Member | Start Date | End Date | Status | Progress (%) | Notes / Risks
Week 1 | Initiation & Planning | Define project scope, objectives, and deliverables | Alex Morgan | 2023-10-01 | 2023-10-07 | Completed | 100% | No major risks identified
Week 2 | Stakeholder Engagement | Conduct requirement workshops with key stakeholders | Sarah Lee | 2023-10-08 | 2023-10-14 | In Progress | 75% | One stakeholder delayed response
Week 3 | Design & Prototyping | Develop UI/UX wireframes and prototypes | David Kim | 2023-10-15 | 2023-10-21 | Pending Approval | 40% | Design feedback loop pending from client
Week 4 | Development Start | Begin coding based on approved design | Maria Lopez | 2023-10-22 | 2023-10-28 | Not Started | 0% | Waiting for final design sign-off
Week 5 | Testing & QA | Conduct internal testing and bug resolution | James Carter | 2023-10-29 | 2023-11-04 | Not Started | 0% | No test environment available yet